## jan 09 - jan 13
Daily Stand-up Meeting Report
Week: jan 09 - jan 13
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori
Revathi Chittepureddy | gathered all requirements from GDP-1 | discussed about iteration plan | created iteration plan | presented iteration plan | have started doing work on application architecture
| analysed all the requirements and about to start implementing with those gathered requirements | as a team worked for iteration plan and decided about future plans | decided who are going to take which part of work | thought about application architecture | have to meet and discuss with the client
| have to get clear idea about next step | have to decide which team member will do what | have to present our iteration plan | no issue | have to work on source code design
Mahesh Babu Kadiyala | gathered all requirements from GDP-1 | discussed about iteration plan | working on application architecture | presented iteration plan | completed application architecture
| Team meeting, reviewed requirements document, worked on iteration plan | worked on aplication architecture | presented iteration plan in class, | worked on appplication architecture and discussed about what classed needed | worked on F01, Discueed about client suggested comments in client meeting
| No obstacles till now | no obstacles | no obstacles | no obstacles | no obstacles
Prudhvi Krishna Tarugu Subbaiah
| I was in excused absence | I was in excused absence | I was in excused absence | I was in excused absence | I was in excused absence
Balaji Vinay Banala | Documented all the requirements gathered | Discussion on development of iteration plan | Developed iteration plan | Presentation of iteration plan | Developed preoject architecture
| Review of requirements document and preparation of iteration plan | completion of iteration plan | Get ready for presentation | Develop project architecture | Develop source code for dispatcher module
| None | None | None | None | None
Kranthi Kumar Mukka
| excused absence | excused absence | excused absence | excused absence | excused absence
Grevil Gonsalo Lopes | Requirements | discussed on iteration plan | created iteration plan | presented iteration plan | initial thoughts on application architecture
| Think on what needs to be done in GDP 2 | worked to create iteraton plan | present iteration plan | think on application architecture | have discussion with client
| No obstacles | No obstacles | No obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## jan 16 - jan 20
Daily Stand-up Meeting Report
Week: jan 16 - jan 20
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | Team meeting, discussed about this week's deliverable artifacts | discussed abt the ui and developing ui | team meeting | worked on user interface | discussed abt dispatcher class
| with our team members discussed about what has to be done as a part of this week | studied swing and trying to implement the ui | discussed on progress ,identification of problems in user interface | Worked on User interface utilizing swing, made classes for track, dispatcher where track class is a model class which will take contributions from the database, for example, track number, most extreme speed of the track | Worked on Dispatcher class using Java swing and also on TrackReader and TrackList class
| no obstacle | no obstacles | small mistakes in drawing using swing | no obstacle | no obstacle
Revathi Chittepureddy | discussed with client about our project plan | have got clear idea that who are working on UI and developing code | started learning java swing | still learning swing | started with UI design of dispatcher
| with our team members discussed about what has to be done as a part of this week | mohammad, prudhvi, grevil are working with me to develop user interface | had team meeting with all team members | started with UI design | started working for dispatcher and track class outline
| have to think more about source code architecture | have started learning java swing | found difficulty to create algorithms | have to think about dispatcher design | no issues
Mahesh Babu Kadiyala | completed application architecture and iteration plan | created tables in database that represents trains and tracks information such as train number, section maximum speed | completed JDBC connection | completed creating of Jframe and Jpanel with correct resolution | completed with track and route file systems
| started working on this weekartifacts such as creating database containing of train and tracks information | creating connection between database and java file using JDBC | started working Graphical user interface for tracks by using swing, here we are using Jframe, jpanel with 1000 resolution inorder to support to our laptop screen | Starte working on creating database in filesystem which includes tracks data , train data and routes information on different files | worked on train filesystem and ready to move on to the writing code for track GUI
| no obstacle | after creating of JDBC connection we realized that, as we have less amount of data, so we are decided to go with filesystem instead of database | no obstacle | no obstacle | no obstacle
Prudhvi Krishna Tarugu Subbaiah | I was in excused absence. | Got clarity on roles who going to work on what like UI and code | Started working with java swing and learnt basics | Had team meeting and got ideas and cleared doubts regarding UI | Learnt creating frames, panels using java swing
| Had discussion with team members about what has to be donw for that week. | Start working with java swing | Attend team meeting for discussing UI | Start creating basic windows, frames and panels with java swing | Implement building windows, frames and panels etc to project UI
| No obstacles | No obstacles | Class and jobs timings clashes for team meetings for all people. | Learning java swing from scratch | No obstacles.
Balaji Vinay Banala | Developed dispatcher module | Decided team member roles | Finished designing database | Worked on developing architecture of source code | Developed architecture of source code
| Division of work between team members | planned to design the database for storing train and track informatino | Develop architecture of source code | Complete architecture of source code | Work on developing required java classes
| None | None | None | None | None
Kranthi Kumar Mukka | excused absence | team meeting regarding assigning tasks and roles | working with java swing basics | cleared few doubts regarding the UI | started working on the UI design
| discussion about the status of project | learn java swing concepts | discussed on UI with team memebers | started working on the project | working on the track and train classes
| none | none | none | none | none
Grevil Gonsalo Lopes | Discussed with client regarding project plan | discussed regarding individual deliverables | started with learning java swing | got doubts on UI clarified | started with UI design
| Discussion regarding what needs to be done this week | start learning java swing | Team meeting for discusion on UI | start with UI design | Start work on Dispatcher and Track classes outline
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## jan 23 - jan 27
Daily Stand-up Meeting Report
Week: jan 23 - jan 27
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | attended class and discussed abt deleverables | worked on dispatcher class and dispatcher ui | had a team meeting | worked on track class and dispatcher ui | attended class and discussed on weekend submissions
| Team meeting, discussed about this week'sdeliverable artifacts, reviewed last week done modules and started working Dispatcher UI class | worked on dispatcher class and Dispatcher UI class, which is main class that will have separate threads trains and tracks, in this class 1st we are initiating the drawing method then one thread launch train class | Team Meeting, discussed on progress, identified the solutions for problems in User interface, regarding database, we are shifting towards file system, extracting data from a text file since we hace limited amount of data. | Worked on Dispatcher UI class to write methods to automate drawing using sections data, modified data of the track class, so that it will take input from this text file | worked on Worklog, effort distribution.
| no obstacle | no obstacle | no obstacle | no obstacle | no obstacle
Revathi Chittepureddy | started working on Dispatcher and track classes outline | started working on dispatcher UI class | working on Jframe and drawing method in java swing class | solved problem with which database to use to store values | started code for automatic track drawing by using track data
| started working on dispatcher UI | source code design is almost done | discussed with problem regarding with database | started code for automatic track drawing | worked on work lo and effort estimation
| no issues | no issues | no issues | no issues | no issues
Mahesh Babu Kadiyala | completed with preparing of filesystems for trains, tracks and routes | In progress with designing track GUI | done with track GUI | in progress with extracting data from file system | done with storing of values in arraylist
| started working on track GUI, this is done by using drawmethod which takes image and coordinates as input | working on track GUI and using fillrect, fillcolor methods for coloring the tracks | extracting data from text file and storing it in arraylist | done with extracting of data from text file and track will take information from this arraylist | working on work log, effort estimation, Worked on driver class which will use swing awt interfaces, Jframe to built window to show our simulator
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Prudhvi Krishna Tarugu Subbaiah | Created dispatcher window | Cleared doubts and got ideas regarding UI | Built two buttons in dispatcher class one for stop button and one for start button. | Got idea on databse like extracting data from text file since we have limited data. | Started code for UI of train using java swing.
| Team meeting for discussing current progress of project and clearing doubts inUI | Build buttons for dispatcher for train user interface using java swing | Team meeting about progress in UI and discussion about database | Start to code for train UI. | Work on worklog and effort distribution.
| Class and jobs timings clashes for team meetings for all people | No obstacles | No obstacles | No obstacles | No obstacles
Balaji Vinay Banala | Started working on java classes | Modified iteration plan | Worked on different class in track package | Worked on trackarray class | Designed database for trackarray class
| Modify iteration plan | Start working on track package | Work on trackarray class | Design database for trackarray class | Design database for route class
| None | None | None | None | None
Kranthi Kumar Mukka | started working on dispatcherUI class | created some methods in the trcak class | created a sample package for moving train image | Added few methods in the track class | discussion regarding the database connection
| working on the track class outline | simultaneously working on the code for moving an object in swing | added JFrame and few methods for creating moving object | worked on the jdbc connection | discussion on how to pass the values from the database
| None | None | None | None | None
Grevil Gonsalo Lopes | Started working on Dispatcher and Track classes outline | started working on dispatcherUI class | added Jframe and drawing method in Java swing class | solved problem with database to be used | started coding for automatic track drawing using track data
| Start working on dispatcherUI class | Add methods to display frame and draw objects | Discuss on problem with database | start to code for automatic track drawing | Work on worklog and effort distribution
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## jan 30 - feb 03
Daily Stand-up Meeting Report
Week: jan 30 - feb 03
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | discussed on week deleverables | prepard for workshop | gave presentation on selinium | worked on dispatcher class | rechecked code and debugged the developed code
| Team meeting: discussed on deliverables this week and team members update on tasks they are working on and problems they are facing. | presented paper on testing and leart abt selinium | Team Meeting, discussed on progress for individual team members. Collectively worked on solution of working of trains. Gave presentation on Workshop 2 | Worked on Dispatcher UI. Dispacther UI class contains project container window which is used to call dispatcher UI from that dispatcher class. | Made changes to code, removed extra code, arranged code and pushed to github
| no obstacles | minor problems in installing selinium and implementing testing | no obstacles | no obstacles | no obstacles
Revathi Chittepureddy | worked on work log and effort distribution | discussed on delivarables | started designing database | I have worked on dispatcher class which contains objects to initialize track reader class. | worked on drawing tracks
| discussed about deliverables of this week | started creating manual drawing of track | discussed on working of trains | i have worked on dispatcher UI which has project container window in which we call dispatcher UI from this dispatcher class | almost done with dispatcher code
| have to start manual track drawing | discussed on functionality of trains that how a train works | manual drawing of trains have been started | have to develop more on manual drawing | no issues
Mahesh Babu Kadiyala | extracting data from text file and stored them in arraylist | worked n designing o track GUI | Done with track GUI | completed with hasmap to map section numbers and station names | done with using of JLabel
| i am designing track GUI with a drawImage method which takes parameters as image, intergers, observer.even we discussed about reading route from text file. | I worked on writing code for track GUI by using drawImage method and also setcolor, fillrect methods inorder to provide coloring to the tracks | Started working on code to map section numbers and station names, it should be done by using hashmap | started working on JLabel in order to display speed of the train | working on Jframe and in order to adjust resolution to support them to our laptop screeen
| no obstacles | No obstacles | No obstacles | No obstacles | No obstacles
Prudhvi Krishna Tarugu Subbaiah | Worked on worklog1 and effort distribution | Discussed current week deliverables | Built basic train model for train UI | Discussed and cleared all doubts and shared thoughts with each team member rearding creating UI of train. | Started building different shapes and changing coordinates for modifying basic rain model using java swing
| Discussion on week deliverables | Build basic train model by building different shapes in java swing | Team meeting discussion on current progress of each individual member and discussing doubts | Build a better train model which looks like a real train regarding UI of train | Complete new train model with appropriate coordinates
| No obstacles. | No obstacles | Class and jobs timings clashes for team meetings for all people | In arranging coordinates while building train model | In arranging coordinates while building train model
Balaji Vinay Banala | Database design for route class | Worked on track reader class | Designed database for track reader class | Worked on developing source code for track reader class | Developed track reader class
| Start working on track reader class | Design database required for track reader class | Implement track reader class | Complete track reader class | Review of java architecture and modify the architecture with required changes
| None | None | None | None | None
Kranthi Kumar Mukka | worked on effort distribution | completed the worklog for submission | discussed on various doubts regarding the project | worked on the tracks part and calculated the cordinates which is time taking | worked with others on the dispatcher module
| worked on worklog | Created a sample package for moving train object | discussed on client meeting | working the track module for building the tracks | developed a moving train object
| None | None | None | None | None
Grevil Gonsalo Lopes | Worked on worklog and effort distribution | Discussed on deliverables and problems facing other team members | Started working on manual drawing of tracks | Had discussion on working of trains | worked on drawing tracks
| Discus on deliverables this week | start working on manual track drawing | discuss on working of trains | work on manual drawing of tracks | clean and organise code and push to github
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## feb 06 - feb 10
Daily Stand-up Meeting Report
Week: feb 06 - feb 10
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | discussed on progress of project | worked on java class of dispatcher | Team Meeting, discussed on client meeting. Discussed changes suggested by client and their implications on project. | worked on creating sectionLengthPixelsArray of dispatcher UI class in order to store all the details of pixel Map objects. | modified stations
| Team meeting: discussed on client meet on Wednesday. Distributed work for getting demonstration ready for client meeet | worked on dispatcher UI class in which added trackPixelMapObject in dispatcher UI class. | worked on changes made by client | worked on dispatcher class | Worked on changing font sizes of station names.
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Revathi Chittepureddy | discussed about UI of tracks | discussed about problems facing till now in order to discuss in client meeting | discussed about outcomes of client team meetings | i have cleared problem regarding how to store track pixel map objects | worked on track module development User Interface of the Dispatcher,
| discussed for wednesday client meeting | last week almost worked on track class | worked on creating trackPixelMap Object in dispatcher UI class | now code is working by storing all track pixel map objects | worked on Architecture of dispatcher, Main modules of the dispatcher
| no issues | have to work on dispatcher UI class | have to think how to store track pixel map objects | had dscussion on outcomes of client meetings and changes suggested by client | have to think about next weeks plan
Mahesh Babu Kadiyala | done with track GUI, adjusting resolution, extracting data from text file and storing it to array list | worked on start and stop buttons | done with start and stop button behavour | worked on client suggested changes such as adding a table on right panel includes information about trains and tracks | done with buttonpanel
| started working on behaviour of emergency stop button and start button by using Jbutton in swing | stilll working on behaviour of start and stop buttons | disussed about cient suggested changes and started working on client suggested changes, such as adding table in right panel that includes train and track information such as section maximum speed and train number | working on stop button fuctionality by using actionlisteners method, and i am placing all these buttons in buttonpanel | working on table on right panel, If user clicks on train number all other information about train should appear in new window.
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Prudhvi Krishna Tarugu Subbaiah | Built new train model for train UI using java swing | Had discussion about client meeting | Started working on moving objects and learnt basics for moving an object or body. | Got clarity on changes suggested by client | Worked on workshop 5, collected data and made ppt.
| Discussion about wednesday client meeting | Start working on moving objects using java swing | Discussion on outcomes of client meet | Working for workshop 5 and make presentation slides for workshop5 | Implement moving object for train model
| Class and jobs timings clashes for team meetings for all people. | No obstacles | Had class unable to meet for discussion | No obstacles | To make whole train model move
Balaji Vinay Banala | Redesigned java architecture | Worked on developing dispatcher class | Added trackPixelMapObject to dispatcher class | Developed dispatcher class | Developed trackDatabase class
| Work on dispatcher class | Work on adding trackPixelMapObject to dispatcher class | Develop dispatcher class | Work on trackDatabase class | Finish all the changes suggested by our client
| None | None | None | None | None
Kranthi Kumar Mukka | discussion about client meeting | Started working on moving objects and learnt basics of swing | discussed about the modifications to be done | worked on the dispatcher UI and added draw line methods | worked on track module development User Interface of the Dispatcher,
| discussion about the integration of code | working with the thread concepts in java swing | added drawline methods in the dispatcher class | added draw string methods for displaying station names | Discussion on outcomes of client meet
| None | None | None | None | None
Grevil Gonsalo Lopes | cleaned and organised code and pushed to github | Had discussion on client meet to be held tomorrow | Worked on UI and removed unused code | had discussion on outcomes and changes suggested by client | researched on topic of workshop 6
| Discuss on Wednesday client meet | Work on UI and remove unused code | discuss on outcomes of client meet | Start researching on topic of workshop 6 | write my part of workshop presentation
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## feb 13 - feb 17
Daily Stand-up Meeting Report
Week: feb 13 - feb 17
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | team meeting to discuss progress | omtimizing the design | team meeting | worked on documents | submission preparation
| Team meeting: discussed on client meet on Wednesday last week. Distributed work for getting changes made to the documents to reflect change. | I have worked on improving the design which we have built earlier and made some changes like changed pixelSize to small so that it could fit in the display. | Team Meeting: discussed on submissions to be made on Friday. Distributed tasks to team members to make and update documents | worked to complete next two stations and freight line for train class | Worked on changes in code. Worked minutes of meeting, issue tracking, worklog, effort estimation, stand up meetings and user manual
| no obstacles | no obstacles | no obstacles | no obstacles
Revathi Chittepureddy | Team meeting: discussed on client meet on Wednesday last week. | made some changes to requirement documents | started changing based on clients suggestion | divided all tasks among team members for friday submission | worked on stand up meetings, effort estimation, work log
| Distributed work for getting changes made to the documents to reflect change. | worked to design train functionality and implementation when working between two stations. | I specifically plan to work on train class, dispatcherUI class and add some classes necessary for writing code for train. I'll also be working on user interface design for dispatcher. | worked to complete next two stations and freight line for train class | working on weekly meetings and integrated all the documents
| have to change according to specification said by our client | have to think about how to implement changes made to requirements | started preparation for fridays submission | started client meetings | submitted friday submissions and thinking about mid semester presentation.
Mahesh Babu Kadiyala | done with buttonpanel that includes start and stop buttons | worked on hasp maps to store section maximum speed | worked on communication between trains and tracks | done with updating next station with the train | done with updating switch direction and next station information
| started working on hasmap to store section number and its maximum speed | started working on running trains and implementation of communication between trains and tracks. Discussed about testing train GUI. | I am reading train image by using drawimage and updating next station by using a method called updateNext, it will check the availability of next section ang passed that information to the train, this code is in progress | I worked on updating next station info and updated direction to the train that code was written in updateDir method, this is done by using switch direction | working on updated requirement documents, worklog, effort estinmaton and standup meeting documents
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Prudhvi Krishna Tarugu Subbaiah | Made train model to move using java swing | Distributed work for getting changes made to the documents to reflect change. | Started working on heart beat signal of train | Divided tasks of friday submission and discussed. | Completed effoert estimation2 and worklog 2 and started standup meetings
| Discussion on last wednesday client meeting | Start working on java multithreading and start working on heart beat signal of train | Team meeting for discussing friday submissions and division of work among team members | Work on worklog2 and effort estimation 2 | Work on test suites and test plan of project
| No obstacles | Need to learn java multithreading and get aware | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | Job timings are effecting my schedule and submission time.
Balaji Vinay Banala | Done with the changes suggested by our client | Gathered the changes | Team came up with the difficulties that will be faced while implementing the changes | Divided the work for the mis semester submissions | shared the documents and validated
| Gather the necessary ways to implement the changes | discussed with the team and gave them the idea how it can be done | Rework on the information gathering to implement changes and divide the work | worked on the submissions | worked on the changes
| None | None | None | None | None
Kranthi Kumar Mukka | discussion about client meeting | discussion about tools supporting software engineering | Team meeting for discussing friday submissions and division of work among team members | worked to complete next two stations and freight line for train class | worked on the installation manual
| worked on the workshop presentation and did some research on my topic | shared our ideas about the workshops | Discuss on submission to be made on friday | worked on the tracks class and added few methods | discussed about the presentation and how should it be done
| None | None | None | None | None
Grevil Gonsalo Lopes | Wrote my part of workshop presentation | made changes to requirements documents | Prepared for presentation | Discussed and divided tasks for Friday submission | Worked on data management plan and use case diagrams
| make changes to document to reflect those suggested by client | prepare for presentation | Discuss on submission to be made on friday | Work on data management plan and use case diagrams | work to integrate documents for submission to professor
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## feb 20 - feb 24
worked on general implementation of multiple threads
Week: feb 20 - feb 24
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | integrated code and solved the integration issues | created threads to implement multiple trains | worked on multiple thread functions | worked on the issues occuring while multiple trains cordination | teasted multiple trains functionality
| worked on fault layer | worked on thread functions | to implement multiple trains | solved the coordination issues | worked on debugging of code for multiple trains
Revathi Chittepureddy | discussed on deliverables this week and team members update on tasks they are working on and problems they are facing. | updating table on right side of dispatcher in order to view details. | worked on table of contents on right side of dispatcher. | have to work functionalities regarding direction of train in which it is heading. | worked on route generation code and integrated code with my team mates who are working on same thing.
| working on building code for freight train. | discussed about heart beat functionality. | discussing about heart beat functionality. | tried some of methods for train direction. | got problems while integrating have to solve it.
| have to change modifications said by the client. | not having clear idea how to implement heart beat functionality. | have to implement some modifications in code. | have to integrate code with the code. | continued to work on code.
Mahesh Babu Kadiyala | worked on the table on right panel, what information should insert in that table and also discussed about how to implement fault layer system | done with implementation of train information in right panel | done with implementation of train and track information in right panel | worked on track module and provided some spce between sections | done with most of the work on right panel
| worked on table on right panel that will contain train and track information such as train number, section number and section maximum speed. | working including track module that includes section number andsection max speed in right panel | worked on track module to provide differentiation between two sections by providing a little bit gap between sections. | worked on highlighting the locked sections with a separate color, and continued to remaining on right panel to include train and section information | worked on arrow mark on running train and impelmenting speed of the train in right panel
| no issues | no issues | no issues | no issues | no issues
Prudhvi Krishna Tarugu Subbaiah | Successfully submitted project components and all submissions. | Had discussion on update of tasks and week deliverables | Worked on testing user interface classes and integrated code. | Organized the code for demonstration | Worked on testing and integration of code
| Team meeting for the discussion on deliverables this week and team members update on tasks they are working on and problems they are facing. | I will Work on testing of all classes of User Interface and also work on integeation part. | Team meeting and discussion on client demonstration and organizing the code for client demonstartion on friday. | Work on testing and integration of code | Start working on multiple passenger train modules based on the created passenger module.
| Class and jobs timings clashes for team meetings for all people | No obstacles | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | No obstacles
Balaji Vinay Banala | worked on general implementation of multiple threads | created threads to represent multiple trains | Worked on thread resume functions | worked on how to create subprocesses in threads | Implemented code to create multiple trains using threads
| created threads to represent multiple trains | Worked on thread resume functions | worked on how to create subprocesses in threads | Implemented code to create multiple trains using threads | Continued to work on the code
Kranthi Kumar Mukka | worked on table of contents on right side of dispatcher. | have to work functionalities regarding direction of train in which it is heading. | Had discussion on update of tasks and week deliverables | Worked on testing and integration of code | Organized the code for demonstration
| discussing about heart beat functionality. | tried some of methods for train direction. | tried some of methods for train direction. | Start working on multiple passenger train modules based on the created passenger module. | Work on testing and integration of code
| have to implement some modifications in code. | have to integrate code with the code. | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | Successfully integrated documents for submission to professor | Worked on fault layer architecture | Worked on fault layer | Worked on integration of code | Worked on testing code for bugs
| work on architecture for fault layer | Continue working on architecture for fault layer | Work on code integration | Test code for bugs | Test code generated by team members
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## feb 27 - mar 03
Daily Stand-up Meeting Report
Week: feb 27 - mar 03
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | worked on testing code created by team mates | learnt integration testing in git hub. | learnt how to integrate code on github | solved intigration problems in the code | discussed on chages suggested by client.
| updated my part on github | tested other code components | integrated code on git hub | demonstrated code to client | worked on implementation of chages mentioned by client
Revathi Chittepureddy | solved problems got due to integration. | intgrated code on github. | integrated code in git hub. | demonstrated our code to professor in class. | discussed on changes mentioned by client to proceed for future events.
| continued to work on multiple passenger trains | learned how to integrate code and update it to git hub. | code demonstration and team meeting to discuss about future events. | client suggested some changes regarding multithreading and collison of trains. | all our team mated divided work among to implement further outcomes.
| have to update code to github. | have to work on methods to improve station and track representation in dispacther. | have to work on changes for represenation of track in dispatcher class. | have to implement changes mentioned by cleint in our code. | have to implement code assigned as a part given.
Mahesh Babu Kadiyala | done with work on right panel and provided arrow mark on the top the train | done with gradual reducing of train when it is stopping | done with integration of trains, tracka dn dispatcher module | worked on pre scheduling of trains to avoid collision | worked on scheduling trains without any conflicts
| worked on passenger train in order to reduce its speed gradually by using coordinate points | worked on integration of train, track and dispatcher modules | working on prescheduling of train with proper schedule | still working on scduling of trains without collision | used locks freight train intersection section to avoid collision with passenger trains
| no issues | no issues | no issues | no issues | no iisues
Prudhvi Krishna Tarugu Subbaiah | Worked on multiple passenger train modules based on the created passenger module. | Worked on the multiple passenger train modules. | Worked on Github, uploaded latest code on Github. | Successfully gave client demonstration | Worked on route section of freight train for highlighting the whole track in which freight train moving.
| Continued to work on multiple passenger train modules. | Work on Github and update code and upload latest code in Github, also integrate the code for Wednesday demonstration. | Code demonstartion and team meeting to discuss about changes suggested about demonstration. | Work on route section of freight train for highlighting the whole track in which freight train moving. | Continued to work on highlighting route section of freight train
| No obstacles | Job timings are effecting my schedule | No obstacles | No obstacles | No obstacles
Balaji Vinay Banala | Continued to work on the code | worked on switch direction | continued to work on switch direction | Worked on blocking routes | continued to work on blocking routes
| worked on switch direction | continued to work on switch direction | Worked on blocking routes | continued to work on blocking routes | continued to work on blocking routes
Kranthi Kumar Mukka | learnt how to integrate code on github | solved problems got due to integration. | Worked on multiple passenger train modules based on the created passenger module. | integrated code in git hub. | discussed on changes mentioned by client to proceed for future events.
| integrated code on git hub | continued to work on multiple passenger trains | Continued to work on multiple passenger train modules. | code demonstration and team meeting to discuss about future events. | continued to work on switch direction
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | Worked on testing code generated by team members | Learned how to integrate code on GitHub | Integrated code on GitHub | Demonstrated our code to professor in class | Discussed on changes suggested by professor
| Learn integration testing on GitHub | Integrate code generated on GitHub | Code demonstration in class | Discuss regarding changes suggested by professor | Work on route generation code
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## mar 06 - mar 10
Daily Stand-up Meeting Report
Week: feb 06 - mar 10
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | worked code for generating route | continued working on generate route function | worked on code for blocking the entire route from source to destination | worked on highlighting roue for freight train | worked on testing the code generated
| continued working on generating route function | integrated my part of route generation code for other teammates on github | highlightting and blocking the entire route for particular train so that other trains cannot interfere | worked with UI team to update the user interface accordint to client requirement | updated and integrated code on github
Revathi Chittepureddy | worked on design architecture changes for automatic route generation | methods to set color have to be implemented | track color have been successfully filled. | I have worked on color for route in which train enters, that color appeared will be green whenever train enters into that particular section | the code in drawPanel.java class have to be merged with code of other team members.
| working on draw panel.java class. | working for multiple trains functionality. | color of track in which train eneters have to enter have to be implemented. | I have used drawImage and setColor methods to accompolish this task | the whole class have been working proplerly after integration.
| have to implement methods in drawPanel.java class | setColor method have to be implemented in the code to fill color of track. | applying methods and studying about each method. | have to discuss about code integration | have to work on fault layer.
Mahesh Babu Kadiyala | worked on pre scheduling of trains | working on multiple trains implemetnation using multi thread concept | worked on multiple trains implemetation | worked on implemtation of multiple trains | done with most part of the multiple trains implemenation
| working on multiple trains implemetation | still working on implementation of trains | getting paths for the trains from pre defined schuling(from database) | worked on 3 trains that travel from boston to reading as well in reverse direction in another route, the route is assigned after pressing of start button where all trains will start, and move in their our route, | worked on multiple trains implemetation with out collision
| no issues | no iisues | no issues | no issues | no issues
Prudhvi Krishna Tarugu Subbaiah | Worked on highlighting route section of freight train | Successfully completed highlighting route section of freight train. | Tested and updated latest code. | Had team discussion about integration of code. | Started working on multiple train functionalities.
| Work on highlighting route section of freight train and complete it | Work on testing code and updated latest code | Team meeting to discuss about integration of code | To start working on multiple train functionalities | Continued to work on multiple train functionalities.
| No obstacles | No obstacles | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | No obstacles
Balaji Vinay Banala | continued to work on blocking routes | worked with UI team to update the user interface accordint to client requirement | Worked on adding new trains | Continued to work on adding new trains such that the code is simple | Continued to work on adding new trains such that the code is simple and avoid deadlocks
| worked with UI team to update the user interface accordint to client requirement | Worked on adding new trains | Continued to work on adding new trains such that the code is simple | Continued to work on adding new trains such that the code is simple and avoid deadlocks | Continued to work on adding new trains such that the code is simple and avoid deadlocks
Kranthi Kumar Mukka | added a method to resize the frame size | made a static table and static information in the dispatcher | discussed about the work done till now | started working on the table to show train details | worked on adding new trains such that the code is simple
| worked on the table to show train details | started working on adding multiple trains | added few comments to the exiting code | also working how the route data is passed to the table | Team meeting to discuss about integration of code
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | worked on code for generating route | Worked on generate route function | Integrated code for the function developed | Discussed with team about integration problems | Started working on multiple trains functionality
| Continue working on generate route function | Integrate code for the function developed | Discuss with team on integration of code and bugs | Start working on multiple trains functionality | Continue work on implementing functionality for multiple trains
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## mar 13 - mar 17
Daily Stand-up Meeting Report
Week: mar 13 - mar 17
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | Discussed with team on process to be used for implementing multiple trains functionality | discussed with team about implementing multiple trains and its basic functionalities | Worked on functionality to increase number of trains in code | Discussed implementation problems with team members | worked with resolving minor errors in code in adding multiple trains
| Work on function to increase the number of trains from current single trains | worked on implementing user interface for multiple trains | worked on multiple trains functionality | integrate code for producing working system with multiple trains | Continued to work on resolving minor errors in code in adding multiple trains
Revathi Chittepureddy | .worked on filling color for station in which train enters. | functionality of each class is working properly and track is taking values from database have been observed. | working on functionality for fault layer . | tried to solve issues regarding train and track communication. | currently working on route generation code.
| acheived last week delivarables | have to work on next upcoming spring to complete overall functionalities | working on how train and track communicates with each other through it | started working on multiple trains based on build source code as an initial part. | have to build code of route in order to not get any collisions.
| integrated code with team members who had already worked on that class. | have to work on fault layer functionality. | have to work on source code architecture for multiple trains. | faced challenges to build algorithm of train routes. | have to start building multiple trains functionality.
Mahesh Babu Kadiyala | completed work on multiple trains implementation | worked on integration | working on integration of train, track and dispatcher modules | worked on integration of multiple modules | working on integration of multiple components
| started working on integration of several projects components, and I found some merge conflits with git and also errors in right panel in dispatcher module, unable to resolve those issues for now | still working on resolving merge conflicts | there are some issues while merging with git | resolved some issues in right panel | changed code as per client suggestion by hitting database once at a time, this avaoids conflits in merging
| some issues with merge conflicts | still have pending issues | conflits while merging | few issues to be resolved | no issues
Prudhvi Krishna Tarugu Subbaiah | Continued to work on multiple train functionalities | Had team discussion about implementing multiple trains and processes to be used. | Worked on implementing user interface for multiple trains. | Had team discussion about progress of multiple trains and problems faced by team members. | Worked on multiple train functionalities
| Team meeting: Discussion on implementing multiple trains and process to be used. | Work on implementing user interface for multiple trains. | Team Meeting: Discussion on progress on multiple trains functionality and discussion on problems faced by team members | Work on multiple train functionalities | Continued to work on multiple train functionalities.
| Class and jobs timings clashes for team meetings for all people | No obstacles | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | No obstacles
Balaji Vinay Banala | Continued to work on adding new trains such that the code is simple and avoid deadlocks | Worked on some deadlock avoidance algorithms | worked with resolving minor errors in code in adding multiple trains | Continued to work on resolving minor errors in code in adding multiple trains | Continued to work on resolving minor errors in code in adding multiple trains
| Worked on some deadlock avoidance algorithms | worked with resolving minor errors in code in adding multiple trains | Continued to work on resolving minor errors in code in adding multiple trains | Continued to work on resolving minor errors in code in adding multiple trains | Continued to work on resolving minor errors in code in adding multiple trains
Kranthi Kumar Mukka | solved issues regarding train and track communication. | Continued to work on multiple train functionalities | Worked on passing the data between trains and tracks | Worked on some deadlock avoidance algorithms | worked with resolving minor errors in code in adding multiple trains
| started working on multiple trains based on build source code as an initial part. | Changed the frame size to add start/stop buttons | worked on displaying the table and route details in the table | worked with resolving minor errors in code in adding multiple trains | Continued to work on resolving minor errors in code in adding multiple trains
| faced challenges to build algorithm of train routes. | no obstacles | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | Worked on implementing funtionality for multiple trains | Discussed with team on process to be used for implementing multiple trains functionality | Worked on functionality to increase number of trains in code | Worked on fucntinality for multiple trains | Discussed implementation problems with team members
| Discuss on process to be used for implementing multiple trains functionality | Work on function to increase the number of trains from current single trains | work on functionality for multiple trains | Discuss implementation problems with team members | integrate code for producing working system with multiple trains
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## mar 27 - mar 31
Daily Stand-up Meeting Report
Week: mar 27 - mar 31
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | worked on testing the code for multiple trains | Had team discussion about meeting with professor and changes made by professor. | worked on errors in implementing multiple trains | Worked on writing the comments of the code | Worked on effort estimation4, worklog4, standup meetings and some part of project components.
| started resolving errors in multiple trains | implemented changes impleted by client | started debugging the entire interated code | Worked on testing the adding multiple trains module | Complete all the submissions and submit documents in project components handling.
Revathi Chittepureddy | worked on analyzing impedances in multiple trains functionality in route generation function. | I worked on expanding the functionality of the single train we had developed to other three trains in our project | worked on UI implementation for multiple trains. | Started analyzing changes to be made in code for avoiding train crashes. | working on weekly or twicley week meetings, client meetings, standup meetings and worklog documents.
| implementing code for multiple trains. | working on code for multiple trains. | have to work upon train crashes. | Worked to expand functionalities of train for multiple trains. | merged with all other documents.
| got problems regarding multiple train collisions. | have to work on UI of multiple trains. | have to work upon functionalities of each train | have to implement suggestion mentioned by client. | submitted all the documents. and cntinued to work on testing part.
Mahesh Babu Kadiyala | worked on merge conflits with git | worked on locking of sectons to avoid conflicts between trains | worked on finding what code to be changed to implement changes such as locking on section | worked on locks on sections | working on locking trains on sections
| as per client suggestion, we are removing pre defined schedule with locking of sections | finding the changes to be made in existing code to implement locks on sections | started working on implementation of locking on sections to avaoid collision between passenger trains along with freight trains conflicts with passenger trains | still working on implementation of locks and blocking that particular route with locks(so that no ther train should access it) | worked on presentation to be made on next week, and some work on testing locks whether they are working properly or not(without collision with other trains)
| no issues | no issues | no issues | no issues | no issues
Prudhvi Krishna Tarugu Subbaiah | worked on testing the developed routes and displaying section numbers on dispatcher window and made changes. | Had team discussion about meeting with professor and changes made by professor. | Tested multiple train functionality code and started working on collision of trains | Had team meeting about progress made by team members and also started finding bugs in project. | Worked on effort estimation4, worklog4, standup meetings and some part of project components.
| Team meeting: discussion about meeting with professor and about the changes, suggestions made by professor about project. | Work on testing multiple train functionalities code and to start work with Grevil about the collision of trains. | Team Meeting: Discussion on changes and progress made by each team members and also problems faced. Also discussed on submissions this Friday and task distribution for submisssion. | Work on effort estimation4, worklog4, standup meetings and some part of project components. | Complete all the submissions and submit documents in project components handling.
| Class and jobs timings clashes for team meetings for all people | No obstacles | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | Job timings are effecting my schedule and submission time.
Balaji Vinay Banala | Continued to work on resolving minor errors in code in adding multiple trains | Worked on the minor changes suggested by client | Continued to work on the minor changes suggested by client | Worked on writing the comments of the code | Worked on testing the adding multiple trains module
| Worked on the minor changes suggested by client | Continued to work on the minor changes suggested by client | Worked on writing the comments of the code | Worked on testing the adding multiple trains module | Continued to work on testing the adding multiple trains module
Kranthi Kumar Mukka | Implemened the methods and coded them to display route details in dispatcher | Worked on few minor changes and fixed the issues | Continued to work on resolving minor errors in code in adding multiple trains | Integrated code and produced a working system | worked on the submissions to be done.
| Resolved few errors in the existing code | Tested the code done till now | Worked on the minor changes suggested by client | Demonstrate code and project to professor | Updated the project management plans and worklog
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | Integrated code and produced a working system | Demonstrated code and running project to professor | Discussed on changes suggested by professor | Started work on bugs identified in project | Worked on submissions to be made today
| Demonstrate code and project to professor | Discuss on changes suggested by professor | Start working on identified bugs in the project | Work on submissions to be made on friday | Submit documents in project components handin and friday iteration plan
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## apr 3 - apr 7
Daily Stand-up Meeting Report
Week: apr 3 - apr 7
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | worked on functionalities of multiple trains | worked on testing of functionalities of multiple trains | worked on integration of code and resolved issues occured in integration | worked on friday submission | gave a end term presentation regarding completed project components
| had a team meeting and discussed on the changes to be made in the project | worked with team members on the modifications to be made in the project | prepared for the presentation on the completed project components | prepared for the end term presentation | discussed regarding the comments of the presentation
Revathi Chittepureddy | worked for safety of freight train without collision | multiple train crahses have been resolved so far. | discussed about integration of code after changes have been made. | working on testing to check whether train is occupying that particular section or not. | worked on integartion and system testing.
| started working on bugs that caused collision | worked on locking system on sections in order to avoid collisons | section locking is implemented in our code | working on integration of the code and started system testing. | discussed about client suggestion regarding table update, train collision.
| have to work more on fucntionalities of freight train. | have to build more accurate safety system. | have to do testing for each individual component | trains are still colliding with each other | working on bugs.
Mahesh Babu Kadiyala | worked on safety at freight train without collision with passenger trains | worked on locking system on sections to avoid collision | discussed about changes done on section locking, whether they met the saety requirements or not, we are decided to test the system with this new design | worked on testing to check only one train is occupying a section at a time | worked on integration and system testing
| started working on implementation of locks on section for each train so that passenger trains doesn't collide with freight train. I am stoppig passenger train one section before freight train comes, we are not controlling freight train, we are just stopping passenger train only | still working on section locking sytem | working on system testing to check only one train is occupying a section at a time, and no passenger train doesnot enter into intersection section if freight train about occupies intersection section | working chages made integration testing and system testing | Got some feedback from the demo presented in class. We controlled the passenger train collsions but should have to control collison with freght train as well
| No obstacles | No obstacles | No obstacles | trains are still colliding with each other | Freight train collision should be controlled
Prudhvi Krishna Tarugu Subbaiah | Completed all the submissions and submitted the documents in project components handling. | Had team meeting and discussed about the progress of project and the changes to be made | Worked on bugs of the project to be discussed on project demonstration | Had team Meeting and discussed on problems in avoiding train collisions and discussed on solutions | Worked on testing, integration of code and also on Friday demonstration of code
| Team meeting: Discussed about the progress of project and the changes to be made | Work on bugs of the project to be discussed on project demonstration | Team Meeting: Discussed on problems in avoiding train collisions and discussed on solutions | Work on testing, integration of code and also on Friday demonstration of code | Work on Friday submission and testing of code
| Class and jobs timings clashes for team meetings for all people | No obstacles | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | Job timings are effecting my schedule and submission time.
Balaji Vinay Banala | Suggested the idea of how to implement locks to the sections. | Implement the locks for freight train | Implement the locks for only one passenger train | Will disbale the functionality of the remaining three passenger trains and work with lock system only on one passenger train. | Included extra variables to double the position of both freight trains and one passenger train to implement the lock system correctly.
| Implement the locks for freight train | Implement the locks for only one passenger train | Will disbale the functionality of the remaining three passenger trains and work with lock system only on one passenger train. | Included extra variables to double the position of both freight trains and one passenger train to implement the lock system correctly. | Implementing the same lock system for the remaining multiple trains after enabling them.
| Trying to get the position of all the remaining passenger trains. | As i considered only one passenger train, the other trains are moving without interruption which is causing collision
Kranthi Kumar Mukka | solved issues regarding train and track communication. | Continued to work on multiple train functionalities | Worked on passing the data between trains and tracks | Worked on some deadlock avoidance algorithms | worked with resolving minor errors in code in adding multiple trains
| started working on multiple trains based on build source code as an initial part. | Changed the frame size to add start/stop buttons | worked on displaying the table and route details in the table | worked with resolving minor errors in code in adding multiple trains | Continued to work on resolving minor errors in code in adding multiple trains
| No obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | Submitted documents for final project handin | Met with team and discussed on changes in project | Worked on code to avoid train crashes | Discussed with team on problems of train collision code | Worked on avoiding train collision
| Meet team and discuss on changes to be made in project | Work on code to avoid train crashes | Discuss with team on problems in solving train collision | Work on avoiding train collision | Work on testing code
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## apr 10 - apr 14
Daily Stand-up Meeting Report
Week: apr 10 - apr 14
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | worked on testing the code | had a team meeting and discussed regarding the bugs araising in the project | worked on resolving issues of trains moving back to the source station | worked on train collision with freight trains | worked on avoiding train collision
| had a team meeting | worked on the updating table for trains and track details | continued working on the train movement | worked on solutions for avoiding train collision | discussed with team abt solution on avoiding collision.
discussed on the issues pointed out in the presentation
Revathi Chittepureddy | worked on client meeting, weekly or twice weekly team meetings. | tried to fix some bugs like multiple train collisions with freight train. | some threads were not functioning properly. | had team meeting discussed about project delivarables. | tried to work on code for multiple train collision.
| we had team meeting and discussed about changes mentioned by the cleint | tried to fix the code dynamically. | tried to work on updating tables automatically. | continued to work on updating table contents like max speed of particular train automatically which is not updating properly. | have to integrate the code which is changed till now.
| got some issues with bugs. have to solve them | have to work on integration problems | worked on solutions for avoiding collisions. | became difficult to set some threads. | have to work on integration problems and to check whether every thing is working propelrly.
Mahesh Babu Kadiyala | Worked on freight train collision with passenger trains | worked on documents to be submitted by the end of next week | worked on final changes in the code to met safety requirements | working on documents | working on changes to be made as per client suggestion
| working on documents to be prepared to submit as a final submission in next week | worked on final changes inoder to met safety requirements at intersection of passenger train and freight train | Worked on documents to be submit by the end of next week such as updated requirements document, stand up meetings, client meetings, requirements specification document | came up with some changes in requirements such as avoiding freight train and fault layer removal. These changes should be reflect in all documents | Worked on changes to be made, in order to reduce conplexity to avoiding freight train, but decided to reian it as it is. If needed we will remove it in final changes, and updated documents by removing fault layer
| No obstacles | No obstacles | No obstacles | No obstacles | No obstacles
Prudhvi Krishna Tarugu Subbaiah | Worked on Friday submission and testing of code | Had team meeting and discussed progress of team members | Worked on generating heart beat of signal | Had team Meeting: Discussed on bug fixing progress of team members and problems faced by them | Continued working on heart beat signal and also worked on Friday submission
| have team meeting to discuss progress of team members | Work on generating heart beat of signal | Team Meeting: Discussion on bug fixing progress of team members and problems faced by them | Continue working on heart beat signal and also work on Friday submission | Work on collision problems of train with team members
| Class and jobs timings clashes for team meetings for all people | No obstacles | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | Job timings are effecting my schedule and submission time.
Balaji Vinay Banala | Implementing the same lock system for the remaining multiple trains after enabling them. | Implementing the same lock system for the remaining multiple trains after enabling them. | Thought of reworking on the code changing the design | Working on rescheduling trains | Working on rescheduling trains
| Implementing the same lock system for the remaining multiple trains after enabling them. | Thought of reworking on the code changing the design | Working on rescheduling trains | Working on rescheduling trains | Making the trains collision free as much as possible.
| Managing multiple train's variables of the lock system. | Changing the code as simple as possible to meet the client requirements |  |  | Difficult to change the staically generated code to dynamically.
Kranthi Kumar Mukka | Working on rescheduling trains | Continue working on code for avoiding deadlock of trains | Discuss with team on members progress on solving bugs | Implementing the same lock system for the remaining multiple trains after enabling them. | some threads were not functioning properly.
| Making the trains collision free as much as possible. | Worked on code for avoiding deadlock of trains | Continue working on collision problem of trains | Added comments to existing code | tried to work on updating tables automatically.
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | Worked on testing code | Discussed with team about overall progress on solving bugs in project | Worked on code for deadlock avoidance | Worked on code for avoiding deadlock of trains | Worked on collision problem of trains
| Discuss with team on members progress on solving bugs | Work on code for avoiding deadlock | Continue working on code for avoiding deadlock of trains | Work on train collision problem | Continue working on collision problem of trains
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## apr 17 - apr 21
Daily Stand-up Meeting Report
Week: apr 17 - apr 21
Project Name: Subway System Simulator
Team Name: Team A - Elite
| Monday | Tuesday | Wednesday | Thursday | Friday
Mohammad Ghori | had a team meeting and discussed about the final submission components | worked on code integration | worked on integration testing | worked on issue tracking document | worked on reflection essay
| worked on solution for avoiding train collision | worked on resolving code integration problems | worked on user mannual | worked on minutes of meeting document | submittes all documents
Revathi Chittepureddy | we had team meeting with team memebers discussed about past week problems | working on integration of the code. | trains are working properly. | had team meeting discussed about project delivarables on friday | worked on team meeting documents.
| working on major problem like collision between freight train and multiple trains. | have to test components which have been changed. | removed fault layer from our project requirements as suggested by our client. | i am working on weekly and twice weekly team meetings. | working on worklog and reflection documents
| tried to implement suggestions said by our client | have to complete testing for train collisions but got some problems. | have to work on some bugs still there to get complete functionality to be done. | have to work on stand up meeting and reflection documents. | documents are ready for submission.
Mahesh Babu Kadiyala | discussed about documents to be prepared to submit as a final submission in this week | working on documents | worked on updation of requirements documents and specification documents | worked on all documents to be submitted by this end of week | working on documents to be submitted by today
| Working on documents to be submitted by the end of this week | worked on documents to be update such as use cases, requirements document, specification documents | We decided to remove freight train(fault layer and heartbeat as well) and designing remaining trains with more safety | Still working documents to be submitting by the end of this week, once again tested the system to confirm about safety requirements. | Worked on reviewing all project documents such as requirement document, use cases, user manual, apart from that working on individual submissions such as work log, estimation effort, reflection essay.
| No obstacles | No obstacles | No obstacles | No obstacles | No obstacles
Prudhvi Krishna Tarugu Subbaiah | Worked on collision problems of train with team members | Had team meeting: Discussed on integration of work of team members | Worked on testing of code, bugs in project and integration of code | Had team meeting: discussed on code integration and submission documents | Worked on work log, effort estimation documents and project component documents
| Team meeting: Discussion on integration of work of team members | Work on testing of code, bugs in project and integration of code | Team meeting: discusseion on code integration and submission documents | Work on work log, effort estimation documents and project component documents | Work on risk analysis, test suites, test plan and stand up meeting documents
| Class and jobs timings clashes for team meetings for all people | No obstacles | Class and jobs timings clashes for team meetings for all people | Job timings are effecting my schedule | Job timings are effecting my schedule and submission time.
Balaji Vinay Banala | Making the trains collision free as much as possible. | Finalizing the changes to the code | Working on the documents to be submitted for the final submission | Working on the documents to be submitted for the final submission | Rechecking the functionalities of the code.
| Finalizing the changes to the code | Working on the documents to be submitted for the final submission | Working on the documents to be submitted for the final submission | Rechecking the functionalities of the code. | Finalizing the documents to submit with one another
Kranthi Kumar Mukka | Working on the documents to be submitted for the final submission | have to test components which have been changed. | discussed about documents to be prepared to submit as a final submission in this week | worked on the project management plans | worked on the reflective essay
| Working on the documents to be submitted for the final submission | have to complete testing for train collisions but got some problems. | Finalizing the changes to the code | worked on the gantt charts | Rechecking the documents done by team
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Grevil Gonsalo Lopes | Worked on collision problems of train | Worked on integrating project code | Worked on integration testing | Worked on document submission on friday | Worked on reflection essay
| Work on integration of project code | Work on integration testing | Work on document submission on friday | Work on reflection essay | Submit final documents
| no obstacles | no obstacles | no obstacles | no obstacles | no obstacles
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?